## Sheet1
Date | Planned Task / Activity | What I Actually Did | Expected Output / Deliverable | Status | % Progress | Actual Issues / Blockers | Action Taken | Next Action | OJT Learning / Notes | Supervisor / Remarks | Weekend handling
WEEK 1 — Hardware Validation + Odoo Foundation ¦ Aug 19 – Aug 24, 2026
2026-08-19 | Set up VS Code + clone IDataProject repo | Done | Repo in C:\IDataProject | Completed | 100% |  |  |  | Done
2026-08-19 | Install Python 3.10 + create venv | Done | venv at backend\venv\ | Completed | 100% |  |  |  | Done
2026-08-20 | Verify Git installation + Docker status | In progress | Git v2.55, Docker installing | Completed | 100% |  |  |  | In progress
CRITICAL BLOCKER - Week 1 Days 1-2
2026-08-21 | Acquire iData T1UHF SDK + documentation |  | SDK folder + docs ready | Not Started | 0% |  |  |  | ACTION ITEM: Get from iData portal
2026-08-21 | Test T1UHF EPC reads (raw, not barcode) |  | Confirmed EPC read capability | Not Started | 0% |  |  |  | Test on device, verify iData T1UHF SDK access
2026-08-21 | Verify Android 13+ SDK compatibility |  | Android 13+ supported confirmed | Not Started | 0% |  |  |  | Check SDK minimum version
2026-08-21 | Test RSSI/power/session/Q-value control |  | All controls accessible | Not Started | 0% |  |  |  | Verify in SDK documentation
Week 1 Continuation (If Hardware Validates)
2026-08-22 | Install Docker Desktop + verify running | Installation in progress | Docker running, docker ps works | In Progress | 50% |  |  |  | Installation in progress
2026-08-22 | Start Docker Compose (Odoo 19 + PostgreSQL) |  | Odoo at localhost:8069 | Blocked | 0% | Blocked on Docker installation | Prepared required compose-mounted files and module paths (backend/odoo.conf, backend/scripts/init-db.sql, stock_barcode_rfid_calibration scaffold); validated compose syntax with docker compose config. | Finish Docker Desktop installation, run docker compose up -d, then verify Odoo on localhost:8069. | Prerequisite files are now in repo, reducing setup friction once Docker is fully available.
2026-08-22 | Verify Odoo admin login (admin/admin) |  | Login successful | Not Started | 0% |  |  |  | Depends on Docker
2026-08-23 | Create .env file from template | Done, using safe dev passwords | .env configured | Completed | 100% |  |  |  | Done, using safe dev passwords
2026-08-23 | Create backend module scaffold | Scaffold verified for stock_barcode_rfid; added stock_barcode_rfid_calibration, backend/odoo.conf, and backend/scripts/init-db.sql | Directory structure ready | Completed | 100% |  |  |  | Scaffold verified for stock_barcode_rfid; added stock_barcode_rfid_calibration, backend/odoo.conf, and backend/scripts/init-db.sql
2026-08-23 | Design data models (rfid.tag.mapping, stock.barcode.rfid.scan, rfid.calibration.profile) |  | Model diagrams + constraints listed | Not Started | 0% |  |  |  | Design doc ready for implementation
2026-08-24 | Create test fixtures (warehouse, product, lot, user, inventory) | Added backend/tests/data/rfid_test_dataset.json and updated backend/tests/conftest.py fixture loaders/factories | 10 test products + 10 test EPCs | Completed | 100% |  |  |  | Added backend/tests/data/rfid_test_dataset.json and updated backend/tests/conftest.py fixture loaders/factories
2026-08-24 | Confirm Phase 0 decisions log | Added IDataProject-Phase0-Decisions.md with scope, hardware, EPC strategy, and Aug 24 deliverables | Phase 0 decisions documented | Completed | 100% |  |  |  | Added IDataProject-Phase0-Decisions.md with scope, hardware, EPC strategy, and Aug 24 deliverables
2026-08-24 | Document hardware validation results |  | Hardware validation report | Not Started | 0% | Pending physical iData T1UHF SDK + device access and on-device validation runs. | Created and committed Phase 0 decisions baseline; tracker now records what is complete vs pending hardware-only items. | Run Aug 21 hardware tasks (SDK acquisition, EPC read, Android 13+, RSSI/power/session/Q-value checks), then write the validation report and go/no-go note. | Hardware evidence remains the gate before moving from setup to validated implementation.
Week 1 checkpoint: Hardware confirmed working OR blocker identified; Odoo 19 running at localhost:8069; module scaffold ready; data models designed + documented; test data created. Status: ON TRACK (if hardware validates). Blocker: Hardware SDK availability (CRITICAL).
WEEK 2 — Core RFID Module (POST /scan + Dedup) ¦ Aug 26 – Aug 29, 2026
2026-08-26 | Implement rfid.tag.mapping model |  | Model in models/rfid_tag_mapping.py | Not Started | 0% |  |  |  | EPC + product mapping, all 3 Ventor scenarios
2026-08-26 | Implement stock.barcode.rfid.scan audit model |  | Model in models/stock_barcode_rfid_scan.py | Not Started | 0% |  |  |  | Audit log for all scans
2026-08-26 | Create database migrations |  | Migrations running, tables created | Not Started | 0% |  |  |  | odoo shell
2026-08-26 | Add database indices (EPC, inventory_id) |  | Queries optimized | Not Started | 0% |  |  |  | Performance baseline
2026-08-27 | Implement POST /stock_barcode_rfid/scan endpoint |  | controllers/main.py complete | Not Started | 0% |  |  |  | Validate EPC, check dedup, resolve product, save audit log
2026-08-27 | Add EPC format validation (96-bit hex, 24-char) |  | Validation working + errors clear | Not Started | 0% |  |  |  | Unit tests passing
2026-08-27 | Implement 2-second dedup logic |  | Dedup window enforced | Not Started | 0% |  |  |  | SELECT with created_at > now()-2sec
2026-08-28 | Write unit tests (EPC validation, dedup, unknown EPC) |  | test_epc_validation.py | Not Started | 0% |  |  |  | pytest running, >=3 tests passing
2026-08-28 | Write integration test (POST /scan -> response) |  | test_rfid_scan_e2e.py | Not Started | 0% |  |  |  | Full workflow tested
2026-08-28 | Test with curl (manual API testing) |  | Postman collection created | Not Started | 0% |  |  |  | curl examples documented
2026-08-29 | Add auth validation (API key check) |  | @auth='bearer' enforced | Not Started | 0% |  |  |  | 401 for missing/invalid key
2026-08-29 | Add error handling (400, 401, 429, 500) |  | All error codes tested | Not Started | 0% |  |  |  | Proper JSON error responses
2026-08-29 | Log all scans to audit trail |  | _logger.info working | Not Started | 0% |  |  |  | Searchable in Odoo logs
Week 2 checkpoint: POST /scan endpoint fully working; dedup logic tested (2-sec window); EPC validation passing; scans recorded in audit log; API documented (Postman collection); unit + integration tests passing. Status: ON TRACK. Dependency: Week 1 hardware validation.
WEEK 3 — Ventor-Reference Mapping Scenarios + Tag Enrollment ¦ Sep 02 – Sep 06, 2026
Scenario 1: Supplier-Provided Tags
2026-09-02 | Create endpoint POST /stock_barcode_rfid/tag_mapping |  | controllers/main.py extended | Not Started | 0% |  |  |  | Request: epc, product_id, encoding_type=supplier
2026-09-02 | Implement Scenario 1 mapping (supplier tags) |  | Supplier tags resolve correctly | Not Started | 0% |  |  |  | EPC matches product.barcode
2026-09-02 | Test: Supplier tag scan -> resolves product |  | test_ventor_scenario_1.py | Not Started | 0% |  |  |  | Scan existing supplier tag, verify status=resolved
Scenario 2: In-House Tag Encoding (NEW)
2026-09-03 | Create endpoint POST /stock_barcode_rfid/write_tags |  | Tag enrollment endpoint ready | Not Started | 0% |  |  |  | Request: product_id, epc_list[]
2026-09-03 | Implement tag writing logic (batch create mappings) |  | Multiple EPCs mapped in one call | Not Started | 0% |  |  |  | Create rfid.tag.mapping for each
2026-09-03 | Add validation: product must have barcode |  | Error if barcode missing | Not Started | 0% |  |  |  | Clear error message
2026-09-03 | Test: Write 5 tags to product, verify in DB |  | test_ventor_scenario_2.py | Not Started | 0% |  |  |  | All 5 EPCs mapped correctly
Scenario 3: Non-Standard EPC (Manual Mapping)
2026-09-04 | Create endpoint PUT /stock_barcode_rfid/tag_mapping/{id} |  | Manual mapping endpoint | Not Started | 0% |  |  |  | Request: serial_number, encoding_type=non_standard
2026-09-04 | Implement serial_number field update |  | Product.serial_number accepts raw EPC | Not Started | 0% |  |  |  | Future scans resolve via serial
2026-09-04 | Test: Manual map EPC to serial, rescan -> resolved |  | test_ventor_scenario_3.py | Not Started | 0% |  |  |  | Unknown EPC -> manual map -> resolved
Unknown EPC Handling (Discrepancy Workflow) - NEW
2026-09-05 | When unknown EPC scanned: status=unknown |  | Unknown EPCs marked with status | Not Started | 0% |  |  |  | Test with non-existent EPC
2026-09-05 | Create UI discrepancy view for unknown EPCs |  | Operator sees list of unknowns | Not Started | 0% |  |  |  | Can copy EPC to product serial_number
2026-09-05 | Operator maps EPC to serial, rescans -> resolved |  | Full discrepancy workflow tested | Not Started | 0% |  |  |  | 3-step: scan -> unknown -> map -> rescan
2026-09-06 | All 3 Ventor scenarios tested end-to-end |  | All tests passing | Not Started | 0% |  |  |  | Comprehensive test suite
2026-09-06 | Update API_CONTRACT.md with actual behavior |  | API contract complete | Not Started | 0% |  |  |  | Document all 3 scenarios
Week 3 checkpoint: Scenario 1 (supplier tags) tested; Scenario 2 (in-house encoding) tested; Scenario 3 (non-standard EPC) tested; unknown EPC discrepancy workflow working; operator can self-map unknown EPCs; all Ventor reference paths validated. Status: ON TRACK.
WEEK 4 — Android Scanner App ¦ Sep 09 – Sep 13, 2026
Prerequisites: Phase 2 API stable (POST /scan working)
iData T1UHF Integration
2026-09-09 | Create IDataUHFReader.kt class |  | android/app/.../IDataUHFReader.kt | Not Started | 0% |  |  |  | Initialize iData T1UHF SDK, start inventory
2026-09-09 | Implement EPC event listener |  | Listener captures EPC + RSSI | Not Started | 0% |  |  |  | rawEpc event handler
2026-09-09 | Add client-side dedup (1-sec window) |  | Local dedup using ConcurrentHashMap | Not Started | 0% |  |  |  | Prevent duplicate POSTs
2026-09-09 | Test: Raw EPC reads on test device |  | EPC logging to logcat | Not Started | 0% |  |  |  | 10+ successful reads
HTTP Client + Offline Queueing
2026-09-10 | Create OdooClient.kt class |  | android/app/.../OdooClient.kt | Not Started | 0% |  |  |  | HTTP client for POST /scan
2026-09-10 | Implement Retrofit/OkHttp configuration |  | HTTP client configured | Not Started | 0% |  |  |  | TLS, API key headers
2026-09-10 | Add offline queue to local SQLite |  | android/app/.../OfflineQueue.kt | Not Started | 0% |  |  |  | Store pending scans
2026-09-10 | Implement retry-on-reconnect logic |  | Syncs when network returns | Not Started | 0% |  |  |  | Auto-sync on WiFi restore
UI + Session Management
2026-09-11 | Create ScanScreen.kt composable |  | android/app/.../ui/ScanScreen.kt | Not Started | 0% |  |  |  | Input inventory ID, display scans
2026-09-11 | Add scan count display (real-time) |  | Counter updates per EPC | Not Started | 0% |  |  |  | Show last EPC received
2026-09-11 | Add Start/Stop scanning buttons |  | UI controls working | Not Started | 0% |  |  |  | Stop button stops reader
2026-09-11 | Add manual sync button (offline queue) |  | Operator can force sync | Not Started | 0% |  |  |  | Clear queue status
Android Tests
2026-09-12 | Unit tests: IDataUHFReader dedup logic |  | test_idata_dedup.kt | Not Started | 0% |  |  |  | 2 same EPCs within 1 sec -> deduped
2026-09-12 | Unit tests: OdooClient request formatting |  | test_odoo_client.kt | Not Started | 0% |  |  |  | JSON request structure correct
2026-09-12 | Integration test: Scan -> POST -> response |  | test_e2e_scan_post.kt | Not Started | 0% |  |  |  | Full workflow mocked
2026-09-13 | Integration test: Offline queue -> sync |  | test_offline_sync.kt | Not Started | 0% |  |  |  | Scans survive offline + sync correctly
Week 4 checkpoint: iData T1UHF reading EPCs; Android app compiles + runs; POST /scan working from Android; dedup on Android side working; offline queue implemented + tested; sync on reconnect working; UI shows real-time scan count. Status: ON TRACK.
WEEK 5 — Calibration Profiles + Offline Handling ¦ Sep 16 – Sep 20, 2026
Calibration Profile Model
2026-09-16 | Create rfid_calibration_profile.py model |  | models/rfid_calibration_profile.py | Not Started | 0% |  |  |  | Power, session, RSSI floor, Q-value
2026-09-16 | Add validation + unique constraints |  | Profile name unique | Not Started | 0% |  |  |  | Error if duplicate name
2026-09-16 | Create database migrations |  | Migrations running | Not Started | 0% |  |  |  | Table created
Calibration Endpoints
2026-09-17 | GET /stock_barcode_rfid/calibration/profiles |  | List all profiles | Not Started | 0% |  |  |  | Used by Android app
2026-09-17 | POST /stock_barcode_rfid/calibration/profiles |  | Create new profile | Not Started | 0% |  |  |  | Request: name, power_dbm, session, rssi_floor
2026-09-17 | PUT /stock_barcode_rfid/calibration/profiles/{id} |  | Update profile | Not Started | 0% |  |  |  | Edit power/session/RSSI
2026-09-17 | DELETE /stock_barcode_rfid/calibration/profiles/{id} |  | Delete profile | Not Started | 0% |  |  |  | Remove unused profile
2026-09-18 | Test: CRUD operations working |  | test_calibration_crud.py | Not Started | 0% |  |  |  | All endpoints tested
Apply Profile to Android
2026-09-18 | Android fetches profiles via GET |  | Profiles list in app | Not Started | 0% |  |  |  | Call GET endpoint on startup
2026-09-18 | Create UI profile selector (dropdown) |  | Operator picks profile | Not Started | 0% |  |  |  | Store selected profile ID
2026-09-18 | Send power/session/Q-value to iData T1UHF SDK |  | SDK receives tuning params | Not Started | 0% |  |  |  | Power/session control working
2026-09-19 | Test: Change power via UI -> verify in SDK |  | iData T1UHF reader responds to param changes | Not Started | 0% |  |  |  | Power changes in real-time
Offline Queue Model
2026-09-19 | Create stock_barcode_rfid_offline_queue.py model |  | models/offline_queue.py | Not Started | 0% |  |  |  | Status: pending/synced/failed
2026-09-19 | Implement sync logic (batch POST) |  | Fetch pending, POST to backend | Not Started | 0% |  |  |  | Mark synced or failed
2026-09-19 | Test: Queue fills when offline |  | test_offline_queue.py | Not Started | 0% |  |  |  | Scans stored locally
2026-09-20 | Test: Sync on reconnect works |  | All pending scans POSTed | Not Started | 0% |  |  |  | Queue cleared after sync
E2E Integration Test
2026-09-20 | Create test_e2e_complete.py |  | Full workflow: scan -> backend -> audit -> calibration | Not Started | 0% |  |  |  | Comprehensive test
2026-09-20 | Test calibration applied mid-scan |  | Power change takes effect | Not Started | 0% |  |  |  | Verified in RSSI values
2026-09-20 | Test offline scenario end-to-end |  | Full offline + sync cycle tested | Not Started | 0% |  |  |  | All scans recovered
Week 5 checkpoint: Calibration profiles stored + queryable; profiles fetchable via API; Android app applies profile; power/session/RSSI tunable via UI; offline queue implemented + syncing; offline scans survive network loss; E2E test passing. Status: ON TRACK.
WEEKS 6-8 — Warehouse Pilot + UAT ¦ Sep 23 – Oct 04, 2026
Pre-Pilot Setup (Days 40-42)
2026-09-23 | Prepare pilot warehouse |  | 20-50 tagged products ready | Not Started | 0% |  |  |  | Physical tags + Odoo entries
2026-09-23 | Create 2-3 calibration profiles for zones |  | Zone A, Zone B, Zone C profiles | Not Started | 0% |  |  |  | Different power/RSSI for each
2026-09-23 | Create test inventory adjustments (5 templates) |  | Ready-to-run adjustments | Not Started | 0% |  |  |  | One per zone
2026-09-24 | Operator training session (4 hours) |  | Operators trained on app + workflow | Not Started | 0% |  |  |  | Hands-on practice
2026-09-24 | Run 2 practice cycles |  | Feedback collected | Not Started | 0% |  |  |  | Bugs identified + fixed
Pilot Week 1 (Days 43-49)
2026-09-25 | Run 5 inventory adjustments with RFID |  | Audit log complete for each | Not Started | 0% |  |  |  | Document scan count, time, discrepancies
2026-09-25 | Measure tag read accuracy |  | Accuracy >=99% | Not Started | 0% |  |  |  | Log misreads if any
2026-09-25 | Measure time vs. barcode scanning |  | 60-70% faster target | Not Started | 0% |  |  |  | Record times
2026-09-26 | Document discrepancies found |  | List all unknown EPCs | Not Started | 0% |  |  |  | Operator maps during pilot
2026-09-26 | Collect operator feedback |  | Notes on usability | Not Started | 0% |  |  |  | What was hard? What was slow?
2026-09-27 | Fix high-priority bugs |  | Bug fixes deployed | Not Started | 0% |  |  |  | Re-test affected workflows
2026-09-27 | Measure scan loss |  | <0.1% target | Not Started | 0% |  |  |  | Count failed POSTs
Pilot Week 2 (Days 50-54)
2026-09-30 | Run 5 more inventory adjustments |  | Verify fixes from Week 1 | Not Started | 0% |  |  |  | All workflows stable
2026-10-01 | Run 4-hour continuous scanning test |  | Measure uptime + stability | Not Started | 0% |  |  |  | 99.5% target
2026-10-01 | Test offline handling (disconnect WiFi mid-adjustment) |  | Scans queue + sync on reconnect | Not Started | 0% |  |  |  | No data loss
2026-10-02 | Verify all scans in audit trail |  | 100% of scans logged | Not Started | 0% |  |  |  | Traceability complete
2026-10-02 | Validate success metrics |  | All targets met | Not Started | 0% |  |  |  | >=99% accuracy, 60-70% speed, 99.5% uptime
2026-10-02 | Create pilot report |  | Signed-off by warehouse manager | Not Started | 0% |  |  |  | Production readiness assessment
UAT Sign-Off (Days 55-56)
2026-10-03 | Security audit (API keys, auth, TLS) |  | OWASP checklist passed | Not Started | 0% |  |  |  | Penetration test ready
2026-10-03 | Performance audit (latency, throughput) |  | <100ms p95 latency | Not Started | 0% |  |  |  | >=50 EPCs/sec
2026-10-04 | Documentation updates (ARCHITECTURE, API_CONTRACT, README) |  | Docs reflect actual behavior | Not Started | 0% |  |  |  | Ready for handoff
2026-10-04 | Create operator runbook |  | Step-by-step procedures | Not Started | 0% |  |  |  | Troubleshooting guide included
2026-10-04 | Sign-off from stakeholders |  | Pilot report approved | Not Started | 0% |  |  |  | Production readiness confirmed
Weeks 6-8 checkpoint: Pilot completed successfully; tag read accuracy >=99%; speed improvement validated (60-70% faster); scan loss <0.1%; uptime 99.5% (4-hour test); operators trained + comfortable; all critical bugs fixed; audit trail complete + verified; production readiness documented. Status: PILOT COMPLETE.
OUT OF SCOPE (next project, not this 8-week pilot): Production Rollout — zone-by-zone deployment (Zone 1: 2 weeks, Zone 2: 2 weeks, full deployment: 2-4 weeks); Receiving/Delivery workflows (Phase 7+).

## Tracker Guide
Tracker Update – Initial Planning & Research
This sheet is a realistic working tracker derived from the 8-week Day-to-Day Action Plan.
Period | Aug 19–20, 2026
Status | Completed as of Aug 19, 2026
Scope | Initial planning and research only; implementation begins Aug 24.
If a task slips, update Status/% Progress and carry the unfinished work into the next action instead of claiming completion.
Completed preparation | Project roadmap review; Odoo 19 Community architecture review; RFID/T1UHF workflow research; OJT schedule preparation; understanding of development, calibration, testing, and pilot phases.
Important | Do not mark Aug 24 onward as completed until the work is actually performed. Weekend rows remain non-working/rest days.
Aug 19–20, 2026 – Actual Preparation Actions | VS Code setup; roadmap verification and planning; verification of the hardware that will be the project's primary focus, specifically the iData T1UHF RFID device.
Preparation Period | Aug 19–20, 2026
Aug 19 | VS Code setup, roadmap verification, and planning.
Aug 20 | Hardware verification and confirmation of the iData T1UHF RFID device as the project focus.
Aug 24 | Formal implementation schedule begins.

## Notes & Red Flags
Daily Standup Template (fill every morning, ~5 min)
Yesterday: Completed: ___ ¦ Fixed: ___ ¦ Tested: ___
Today: Implement: ___ ¦ Test: ___ ¦ Debug: ___
Blockers: None / Hardware-SDK issue / Odoo API issue / Other: ___
Critical Red Flags (stop & escalate)
Week 1: iData T1UHF SDK missing or incompatible -> Escalate to OJT supervisor immediately. No fallback hardware is locked for this project — do not silently swap vendors (e.g. to Zebra) without sign-off.
Week 2-3: Dedup race condition (same EPC not always marked duplicate) -> Add a database lock or cache (Redis).
Week 4: Offline sync loses scans -> Add transaction handling + recovery logic.
Week 5-6: Pilot shows <95% accuracy -> Recalibrate (RSSI floor, power, Q-value) before proceeding; do not raise power/loosen RSSI just to hit a deadline.
Any week: Operator feedback shows a critical UI issue -> Hot-fix before continuing.
Success Metrics by Week
Week 1: Hardware validation = Pass all checks
Week 2: POST /scan = 100% test pass rate
Week 3: All 3 Ventor-reference scenarios = Tested
Week 4: Android app = Scans POST to backend
Week 5: Offline + Calibration = E2E passing
Weeks 6-8: Pilot = Accuracy >=99%, Speed 60-70% faster, Uptime 99.5%
Final Notes
This tracker reflects the current confirmed direction: Odoo 19 Community, iData T1UHF only (no Zebra), Ventor-style recognition UX (scan -> resolved product -> live in Inventory) via a custom Android app + custom Odoo scan endpoint/UI — not Odoo's native Barcode app, which is Enterprise-only. EPC resolution follows the Ventor PRO reference pattern (ventor.app), used as a UX/workflow guide only.
Key differences from the earliest draft: hardware validation moved to Week 1 (was Week 5-6); rfid.tag.mapping model + product Barcode/Serial Number fields used for EPC resolution; tag enrollment (POST /write_tags) added in Week 3; all 3 Ventor-reference scenarios implemented; unknown-EPC discrepancy workflow added; scope is an 8-week validated pilot ending at Pilot/UAT, not production; workflow scope is Inventory Adjustments only.
Tracker status: ready for Week 1 execution. Next: hardware validation (critical path item).