## Tracker
Date | Planned Task / Activity | What I Actually Did | Expected Output / Deliverable | Status | % Progress | Actual Issues / Blockers | Action Taken | Next Action | OJT Learning / Notes | Supervisor / Remarks | Weekend/Holiday Handling
2026-08-24 | Confirm Phase 0 decisions log against locked constraints (T1UHF-only, Community, rfid.tag.mapping, Pilot/UAT scope). | Confirmed via chat: T1UHF-only, Community edition, Pilot/UAT scope, and (until the 2026-08-26 pivot) the rfid.tag.mapping design all cross-checked against rfid-odoo-roadmap-MASTER.docx Section 2 before any code was written. | Signed-off Phase 0 decisions matching rfid-odoo-roadmap-MASTER.docx Section 2. | Done | 100 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-08-25 | Set up / verify Docker Compose (Odoo 19 + PostgreSQL); confirm containers healthy. |  | Odoo 19 running at localhost:8069; docker ps shows healthy containers. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-08-26 | Scaffold stock_barcode_rfid Odoo module (manifest, models/, controllers/, views/, security/, tests/). | Manifest, models/ (rfid.tag.mapping, stock.barcode.rfid.scan), controllers/ (POST /stock_barcode_rfid/scan), security/ir.model.access.csv all built and pushed. Module later marked inactive by the 2026-08-26 pivot -- code retained, not deleted. | Empty module installs without errors. | Done (module inactive -- see 2026-08-26 addendum) | 100 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-08-27 | Configure product.product Barcode (EAN-13/14) and Serial Number fields for EPC matching. Do NOT configure Barcode Nomenclature. |  | Barcode/Serial Number fields verified as the EPC match targets on a test product. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-08-28 | Scaffold Android project (Kotlin); package structure; Git branch strategy. | Per Desktop 1: an Android app (RfidScannerApp2, Java, package com.manilainvestments.rfidscanner, using UHFManager/UM_MODULE) has started -- exact current state not yet confirmed against this repo. | Android project builds; repo structure matches monorepo convention. | In Progress | 25 | Real app lives in a separate session (Desktop 1), not yet merged into this repo. This repo's android/ folder is still the older, unrelated Kotlin skeleton (com.idataproject). |  | Confirm RfidScannerApp2’s current state with Vin and merge the real project files into this repo’s android/ folder. |  | Pending
2026-08-31 | HOLIDAY — No work scheduled |  |  | N/A | 0 | [5 empty] | National Heroes Day (Regular Holiday, Proclamation No. 1006)
2026-09-01 | Source and import the iData T1UHF SDK (.aar/.jar); resolve Gradle dependencies; smoke-test SDK init on the physical device. | UHFJar_V1.4.05.aar + native libs (libjni_rfid_driver.so, libserialportJni.so for arm64-v8a/armeabi-v7a) identified as the correct iData-branded SDK (of 3 IT-provided candidates) and committed into android/app/libs and jniLibs. Demo APK (UHFDemo_v1.2.534) provided for on-device sideload. Smoke test on the physical T1UHF unit not yet confirmed back. | SDK initializes; device responds to open()/powerOn()-equivalent call. CRITICAL PATH ITEM. | In Progress | 50 |  |  | Sideload UHFDemo_v1.2.534 APK onto the physical T1UHF and confirm scan/inventory works. |  | Pending
2026-08-26 | ARCHITECTURE PIVOT LOGGED: per direction, switched from the custom stock_barcode_rfid controller/rfid.tag.mapping design to direct Android -> Odoo XML-RPC/JSON-RPC integration (matching EPC against stock.lot.name), per Desktop 1’s Option 3. | Added Section 9 addendum to rfid-odoo-roadmap-MASTER.docx documenting the override and the reintroduced unknown-EPC gap; marked backend/stock_barcode_rfid/ inactive; rows below for the old architecture are flagged Superseded rather than deleted. | Roadmap addendum committed; tracker rows 10-23 below annotated. | Done | 100 | Rows 10-23 describe the superseded custom-controller design; some were already built before the pivot decision and are flagged accordingly rather than rewritten. | Documented pivot in roadmap Section 9 and this tracker row. | Confirm/implement direct XML-RPC client and stock.lot.name matching on the Android side (Desktop 1 has the working reference). | See rfid-odoo-roadmap-MASTER.docx Section 9 for full rationale.
2026-09-02 | Build rfid.tag.mapping model: epc (unique, indexed), product_id (required), barcode, serial_number, encoding_type (supplier/in_house/non_standard), lot_id (OPTIONAL — must never be required). |  | models/rfid_tag_mapping.py complete; migration creates table; lot_id confirmed optional in constraint tests. | Done (module inactive -- see 2026-08-26 addendum) | 100 | Built 2026-08-26, before the pivot decision. Code retained in backend/stock_barcode_rfid/ (now marked inactive) rather than deleted -- see roadmap Section 9. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-03 | Build stock.barcode.rfid.scan audit model: epc, rssi, tag_mapping_id, product_id, lot_id, status (resolved/unknown/discrepancy), session_id, inventory_id, timestamps. |  | models/stock_barcode_rfid_scan.py complete; migration verified in psql. | Done (module inactive -- see 2026-08-26 addendum) | 100 | Built 2026-08-26, before the pivot decision. Code retained in backend/stock_barcode_rfid/ (now marked inactive) rather than deleted -- see roadmap Section 9. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-04 | Basic iData T1UHF scan loop: powerSet, sessionModeSet, inventoryModelSet, readTagFromBuffer; log raw EPCs to logcat. |  | 10+ real tags read; raw EPCs logged. No Zebra/DataWedge classes anywhere in the diff. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. | SDK confirmed 2026-08-26: UHFJar_V1.4.05 (iData-branded, from the UHF开发包_V2.2 package) integrated into android/app/libs and jniLibs; demo APK provided for on-device validation. See android/SDK_NOTES.md. | Pending
2026-09-07 | Add DB indices (unique EPC, inventory_id) and constraints; write model-level unit tests. |  | Indices created; test_rfid_tag_mapping.py passing. | Done (module inactive -- see 2026-08-26 addendum) | 100 | Built 2026-08-26, before the pivot decision. Code retained in backend/stock_barcode_rfid/ (now marked inactive) rather than deleted -- see roadmap Section 9. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-08 | Implement POST /stock_barcode_rfid/scan: EPC lookup against rfid.tag.mapping, resolved/unknown status, audit log write. |  | curl POST returns correct status field for both a known and an unknown EPC. | Done (module inactive -- see 2026-08-26 addendum) | 100 | Built 2026-08-26, before the pivot decision. Code retained in backend/stock_barcode_rfid/ (now marked inactive) rather than deleted -- see roadmap Section 9. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-09 | Implement API key authentication: auth='public' at the route, manual Odoo API-key check against res.users.apikeys inside the controller (NOT auth='bearer'). |  | Missing/invalid key -> 401; valid key -> request proceeds as that user. | Superseded (see 2026-08-26 addendum) | 0 | Not applicable under direct XML-RPC -- auth is via the Odoo user’s own credentials, not a custom API key. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-10 | Implement 2-second server-side dedup (EPC + timestamp window). |  | Rapid double-scan of the same EPC is marked is_duplicate on the second call. | Superseded (see 2026-08-26 addendum) | 0 | Not applicable under direct XML-RPC -- no server-side controller to dedup at. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-11 | Write integration tests: valid EPC resolves, unknown EPC marked unknown, dedup within/after 2s window. |  | tests/test_rfid_scan_endpoint.py — all cases passing. | Superseded (see 2026-08-26 addendum) | 0 | Not applicable -- tested the superseded controller path. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-14 | Scenario 1 (supplier pre-encoded): resolve via product.barcode match; test against a real barcoded product. |  | Supplier-style tag resolves to the correct product on scan. | Superseded (see 2026-08-26 addendum) | 0 | Not applicable as written -- scenario still relevant conceptually, but resolution now happens via stock.lot.name lookup, not a controller endpoint. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-15 | Scenario 2 (in-house): POST /stock_barcode_rfid/write_tags — batch-create rfid.tag.mapping rows for a product + EPC list. |  | Batch write of 5 EPCs creates 5 mappings; all rescan as resolved. | Superseded (see 2026-08-26 addendum) | 0 | Not applicable as written -- see note on row 18. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-16 | Scenario 3 (non-standard EPC): endpoint to write serial_number onto an rfid.tag.mapping row; rescan resolves. |  | Unknown EPC -> operator adds serial_number -> rescan status flips to resolved. | Superseded (see 2026-08-26 addendum) | 0 | Not applicable as written -- see note on row 18. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-17 | Discrepancies view: list all stock.barcode.rfid.scan rows with status='unknown' for operator resolution (Ventor 'Discrepancies' pattern). | Replacement built: UnresolvedScanStore.kt (local SQLite) logs every EPC that fails to match, so operators can still review unresolved tags. This is the on-device equivalent of the original server-side Discrepancies view. | View shows unresolved EPCs with product context where available. | Superseded -- replacement implemented (see 2026-08-26 addendum) | 100 | Replaced: unresolved/unmatched EPCs are now logged on-device via UnresolvedScanStore (android/app/.../scanner/UnresolvedScanStore.kt) instead of a server-side Discrepancies view. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-18 | Session/stream mechanism (SSE or long-poll) relaying resolved scans into a custom scan UI stub. |  | Manually POSTed EPC appears in an open browser session within ~1-2 seconds. | Superseded (see 2026-08-26 addendum) | 0 | No API contract needed -- Android talks to Odoo’s existing XML-RPC/JSON-RPC API directly, not a custom endpoint. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-21 | Update API_CONTRACT.md with the corrected auth pattern and all 3 mapping scenarios. |  | Contract doc matches actual controller behavior; ready for Android integration. | Superseded (see 2026-08-26 addendum) | 0 | API_CONTRACT.md not applicable under direct XML-RPC. Android-side client should be an OdooXmlRpcClient (or JSON-RPC equivalent) instead of the OdooClient.kt/POST-/scan design originally planned here. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-22 | Android: OdooXmlRpcClient.kt -- direct XML-RPC/JSON-RPC client to Odoo (no custom controller); resolves EPCs against stock.lot.name, writes stock.quant/stock.move directly. Wire UnresolvedScanStore.logUnresolved() on any lookup with no matching stock.lot. |  | Manual test screen sends a real EPC to Odoo and gets a JSON response back. | Not Started | 0 | Original plan (POST /scan + API key) superseded by the 2026-08-26 Option 3 pivot -- see roadmap Section 9. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-23 | Android: client-side dedup (in-memory, tunable window) on top of the T1UHF scan loop. |  | Same EPC scanned twice rapidly only POSTs once. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-24 | Android: RSSI-based filtering exposed as a tunable setting; batch-and-throttle logic to the bridge. |  | Weak-signal reads suppressed below a configurable RSSI floor. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-25 | Android: offline queue (Room/SQLite) — buffer scans on Wi-Fi drop, resync on reconnect. |  | Simulated disconnect: scans queue locally, then flush and clear on reconnect. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-28 | Android: operator UI (Jetpack Compose) — live scan count, last EPC, start/stop, manual sync, connection-health indicator. |  | UI reflects live state during a real scan session. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-29 | Build rfid.calibration.profile model: name, power_dbm, session, rssi_floor_dbm, q_value, zone — iData T1UHF ranges only, no Zebra references in help text. |  | Model + CRUD endpoints (GET/POST/PUT/DELETE) complete and tested. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-09-30 | Android: calibration-preset selector; apply profile values to the T1UHF SDK calls (powerSet/sessionModeSet/inventoryModelSet). |  | Selecting a profile visibly changes RSSI behavior on the device. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-01 | Freeze Android feature set; confirm offline queue + resync is stable end-to-end before calibration begins. |  | Offline -> queue -> reconnect -> sync cycle passes with zero data loss across 3 repeated trials. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-02 | Calibration Step 1–2: baseline max-power/Session 0 read radius; power sweep in ~4dBm steps to find lowest complete-read power. |  | Worst-case over-read radius and candidate minimum power documented. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-05 | Calibration Step 3–4: sweep Session 0→1→2; test Multi-label / Adaptive / Fast-read modes. |  | Best session + inventory mode for the shelf/scan pattern documented. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-06 | Calibration Step 5–6: RSSI-floor sweep; combined-settings A/B vs. manual count across 5+ trials, varied shelf densities. |  | Accuracy % and time-savings % documented against the ≥99% / 60-70% targets. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-07 | Calibration Step 7–8: throughput tuning (Q-value, EPC-only reads, batch sizing) — power/session/RSSI floor untouched; re-run the Step 6 accuracy A/B. |  | Throughput improved with zero accuracy regression, or rolled back and re-tested until it is. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-08 | Finalize and bake the accuracy-validated calibration profile into the Android app as the default preset. |  | Written calibration profile live in the shipped app build. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-09 | Full E2E test: RFID scan -> Android dedup -> direct XML-RPC/JSON-RPC to Odoo -> stock.lot.name match -> stock.quant adjustment, verified against stock.move history. (Originally routed through a custom Odoo bridge + scan UI -- superseded, see roadmap Section 9.) |  | End-to-end flow verified; every scan traceable in stock.barcode.rfid.scan. | Not Started | 0 | Path corrected from 'Odoo bridge -> scan UI' (superseded architecture) to direct XML-RPC. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-12 | Multi-user + failure-mode testing: two concurrent sessions (no cross-talk), server restart mid-scan, network drop, garbage EPC. |  | All failure modes handled gracefully; documented in the known-issues list. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-13 | Load + security + performance pass: 200+ tag dense-shelf sweep, verify the Odoo user account used for XML-RPC has least-privilege access (not an admin account), latency check on the XML-RPC round trip (<100ms p95, >=50 EPCs/sec). (Originally an auth-bypass test against a custom /scan endpoint -- not applicable, no such endpoint exists under the current architecture.) |  | Load/security/performance report against all three targets. | Not Started | 0 | Security test target corrected -- no /scan endpoint exists to bypass under direct XML-RPC; real risk is XML-RPC credential scope instead. |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-14 | Prepare pilot warehouse zone: tag 20-50 real products; create 2-3 zone calibration profiles; stage inventory adjustment sessions. |  | Physical tags + Odoo entries ready; zone profiles created. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-15 | Operator training session; run 2 practice inventory-adjustment cycles before the shadow-run. |  | Operator can run a full cycle unassisted; practice bugs logged. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-16 | Shadow-run Days 1–3: log RFID counts as non-authoritative; compare against manual counts; track calibration drift vs. lab conditions. |  | Daily accuracy comparison recorded; drift from Phase 4 lab numbers documented. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-19 | Collect operator feedback (ergonomics, scan speed, false reads); adjust calibration profile if floor conditions require it. |  | Feedback summary; any profile adjustments documented and re-validated. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending
2026-10-20 | Compile go/no-go decision using real pilot accuracy numbers; finalize documentation; log Production Rollout backlog items for handoff. |  | Signed-off pilot report with go/no-go decision — OJT deliverable complete. | Not Started | 0 |  |  | See rfid-odoo-roadmap-MASTER.docx for phase context. |  | Pending

## Tracker Guide
Purpose | Single authoritative 8-week/2-month schedule for the OJT RFID-to-Odoo pilot, ending at Pilot/UAT sign-off.
Source of truth | Task content and phase order are derived from rfid-odoo-roadmap-MASTER.docx. If this tracker and that document ever disagree, the roadmap document wins.
Architecture pivot (2026-08-26) | Per direction, the custom stock_barcode_rfid controller architecture in Section 2 was overridden by Desktop 1's Option 3 (direct XML-RPC from the Android app). Tracker rows describing the old design are marked Superseded or Done (module inactive) rather than deleted. Full rationale in rfid-odoo-roadmap-MASTER.docx Section 9.
Holiday handling | Philippine 2026 public holidays per Proclamation No. 1006 are shown as explicit HOLIDAY rows (not silently skipped), so the schedule is auditable. National Heroes Day (Aug 31, 2026) is the only regular holiday inside the project window.
EPC mapping model | ORIGINAL DESIGN (superseded, code retained inactive): rfid.tag.mapping + standard Barcode/Serial Number fields on product.product. CURRENT (as of 2026-08-26 addendum): direct match against stock.lot.name via XML-RPC/JSON-RPC from the Android app (no custom Odoo controller). This reintroduces the unresolved/unknown-EPC gap the original design existed to avoid; that gap is now handled on-device via UnresolvedScanStore (android/app/.../scanner/UnresolvedScanStore.kt), not server-side. See rfid-odoo-roadmap-MASTER.docx Section 9.
Hardware | iData T1UHF exclusively. Any Zebra or DataWedge reference appearing in future edits of this tracker is contamination and should be removed on sight.
Auth pattern | ORIGINAL DESIGN (superseded, code retained inactive): Odoo API key checked inside the controller (auth='public' + manual header check against res.users.apikeys). auth='bearer' is not a real Odoo route auth type. CURRENT: not applicable -- the Android app authenticates to Odoo's XML-RPC/JSON-RPC API directly as an Odoo user, no custom API key scheme.
Scope boundary | Ends at Pilot/UAT go/no-go. Production Rollout is explicitly out of scope for this OJT engagement and is not scheduled here.
Status values | Completed / In Progress / Not Started / Blocked / N/A (holiday rows).
% Progress | 0 / 25 / 50 / 75 / 100.