# Odoo v19 × iData T1UHF RFID

## Inventory Integration — Master Roadmap (Rev. 2)

Revision note: This document supersedes rfid-odoo-roadmap-FINAL.docx and ROADMAP_UPDATED.md as the single authoritative architecture reference. It consolidates and corrects both, and formalizes the Ventor PRO RFID workflow as the UX/behavior reference for the custom Community-edition build.

Last Updated: 2026-08-23   |   Scope: OJT Pilot/UAT (8 weeks)   |   Production Rollout: explicitly out of scope

# 0. Project Summary

Goal: Give iData T1UHF RFID scans the same instant-recognition, live-reflected-in-Odoo experience Ventor PRO delivers on its supported hardware — but built as a custom Android app plus a custom Odoo scan surface, because Odoo v19 Community does not include the native Barcode app (stock_barcode) or Enterprise's Barcode Nomenclature-driven RFID path that Ventor itself relies on.

## Success Criteria

- RFID scans are recognized against known products and reflected live in a custom Odoo scan UI covering Inventory Adjustments (Receipts/Deliveries are architecturally supported but out of pilot scope).

- Bulk-read accuracy ≥ 99% against ground-truth counts in the calibrated read zone, with near-zero false cross-reads from adjacent bins.

- Full-shelf inventory count time reduced 60–70% vs. barcode-by-barcode scanning.

- System is stable enough for a supervised warehouse pilot — not a demo.

- Unknown/unmapped EPCs are never silently dropped — they are logged with status = unknown and resolved through an operator mapping workflow (Ventor's “Discrepancies” pattern).

## Stack

Android (Kotlin, iData T1UHF SDK)  ·  Odoo 19.0 Community (Python, ORM, OWL/JS)  ·  PostgreSQL  ·  self-hosted Docker.

# 1. Architecture — Ventor as Reference, Not Dependency

Ventor PRO is the UX and workflow north star. It is not installed, imported, or depended on anywhere in this project — it's a commercial Enterprise-and-Community app maintained by VentorTech, referenced here purely as a proof that this class of workflow (EPC → product resolution → live inventory update, with a graceful path for unrecognized tags) is a solved, validated UX pattern on Odoo. The table below maps each Ventor RFID behavior to how it is reproduced with iData T1UHF + custom code on Community.

| Ventor PRO RFID behavior | How it works in Ventor | Our Community-compatible implementation |
| --- | --- | --- |
| Tag enrollment (“Write Tags”) | Operator picks a product with an existing Odoo barcode, scans blank tags, taps WRITE TAGS — tags are encoded EAN-14 in one pass. | POST /stock_barcode_rfid/write_tags: operator selects product_id + scans EPCs; app creates rfid.tag.mapping rows with encoding_type=in_house. No physical tag writing constraint differs — same operator flow. |
| Standard EPC resolution | Ventor decodes EAN-14 from the tag and matches it to the product's Odoo Barcode field (EAN-13) automatically — no manual reformatting needed. | rfid.tag.mapping.barcode stores the associated EAN-13/14 value; POST /scan looks up rfid.tag.mapping by epc first (exact match, O(1) via unique index), falling back to a normalized barcode comparison if needed. |
| Non-standard / undecodable EPC | Tag's EPC doesn't map to a barcode. Operator copies the raw EPC into the product's Serial Number field in Odoo; rescanning then resolves it. | Same operator action, but written to rfid.tag.mapping.serial_number (encoding_type=non_standard) rather than directly onto product.product, so the mapping is auditable and reversible without touching product master data. |
| Unresolved tag handling (“Discrepancies” + Tag Locator) | Scans that don't resolve appear in a Discrepancies list; operator can locate and resolve them later. | stock.barcode.rfid.scan.status = 'unknown' on any scan with no matching rfid.tag.mapping. A discrepancy view lists these; operator maps and rescans — functionally identical outcome. |
| Inventory Adjustment scanning screen | Native Ventor PRO menu: scan location, then items; live count and theoretical-vs-counted quantity shown. | Custom OWL/QWeb view against the same stock.inventory model, fed live via SSE/long-poll from the Odoo bridge module (see Phase 2). No dependency on stock_barcode's barcode_scanned event bus, which is Enterprise-only. |

Why not just use Ventor? Ventor PRO is a paid, closed-source mobile app; it is not a fit for an OJT deliverable that must produce original, evaluable Android + Odoo code, and its RFID feature list (per VentorTech's own release notes) is built around Zebra RFID sleds/handhelds, not the iData T1UHF SDK this project is locked to. It remains the correct reference for “what good looks like,” not a component of the system.

## High-Level Data Flow

[iData T1UHF Handheld]
   iData SDK reads tag -> EPC (96-bit, 24 hex chars)
        |
[Android App (Kotlin)]
   Client-side dedup (time-window) -> RSSI filter -> batch
   POST /stock_barcode_rfid/scan  (EPC, session_id, inventory_id, rssi)
        |
[Odoo 19 Community - stock_barcode_rfid module]
   Server-side dedup -> rfid.tag.mapping lookup
   resolved  -> stock.move.line / stock.quant update, push to scan UI (SSE)
   unknown   -> stock.barcode.rfid.scan(status='unknown') logged, surfaced in Discrepancies view
        |
[Custom OWL/QWeb Scan UI]
   Live count, theoretical vs. counted, manual discrepancy resolution

# 2. Locked Decisions Log

This table is authoritative. Any document, code comment, or task description that contradicts it is wrong and should be corrected on sight.

| Decision | Locked choice | Rationale |
| --- | --- | --- |
| Odoo version / edition | 19.0 Community | No Enterprise subscription. stock_barcode and Enterprise Barcode Nomenclature-driven RFID are unavailable — confirmed hard constraint. |
| Hardware | iData T1UHF exclusively | Not T2UHF, not Zebra, not DataWedge. Any Zebra/DataWedge reference in code, docs, or trackers is contamination and must be purged on sight. |
| EPC ↔ product mapping | Custom rfid.tag.mapping model, reusing standard Barcode (EAN-13/14) and Serial Number fields on product.product | Barcode Nomenclature cannot represent status='unknown'; it silently fails to match rather than flagging a resolvable discrepancy. This was the deciding factor. |
| In-Odoo scan UI | Custom ORM-driven OWL/QWeb view in stock_barcode_rfid, fed via SSE/long-poll | stock_barcode's barcode_scanned event bus is Enterprise-only and unavailable on Community. |
| Workflow priority | Inventory Adjustments first | Lowest risk, best proving ground; Receipts/Deliveries are architecturally supported but out of pilot scope. |
| Scope boundary | Ends at Pilot/UAT sign-off (8 weeks / ≈ 2 months) | OJT placement scope. Production Rollout (infra hardening, phased zone rollout) is explicitly deferred, documented only as Phase 7 backlog. |
| Hosting | Self-hosted Docker (dev + pilot) | Full control, no SaaS lock-in; production-grade infra (HTTPS, backups, monitoring) is Phase 7, out of scope. |
| Contingency path | Local SQLite buffer + scheduled XML-RPC/JSON-RPC sync | Fallback if the custom OWL scan UI stalls; XML-RPC/JSON-RPC is identical across Community/Enterprise, so this path has zero edition risk. |
| Dedup strategy | Client-side (Android, short window) + server-side (2-second window) | Resilient to network retries and rapid re-scans without double-counting stock. |
| API authentication | Odoo API key (res.users API key) validated inside the controller; auth='public' at the route level with manual header check | Odoo's @http.route auth parameter does not natively support a 'bearer' auth type — that has to be implemented, not declared. See Section 5. |

# 3. Phased Roadmap

## Phase 0 — Discovery & Requirements Lock — COMPLETE (Week 1)

- Odoo version/edition confirmed: 19.0 Community, self-hosted Docker.

- Hardware confirmed: iData T1UHF handheld, exclusively.

- EPC ↔ product mapping approach locked: rfid.tag.mapping + standard Barcode/Serial Number fields.

- Workflow priority locked: Inventory Adjustments first.

- Scope boundary locked: Pilot/UAT only, Production Rollout deferred.

Deliverable: this document + the corrected tracker, both signed off as the project's source of truth.

## Phase 1 — Environment & Foundations (Week 1–2)

- Docker Compose dev environment: Odoo 19 + PostgreSQL running.

- Odoo module scaffold: stock_barcode_rfid (manifest, models, controllers, security, views).

- Configure product.product Barcode / Serial Number fields for EPC matching (NOT Barcode Nomenclature — see Section 2).

- Android project scaffold (Kotlin), Git branch strategy.

- Source and integrate the iData T1UHF SDK (.aar/.jar) into the Android Studio project; smoke-test SDK init against the physical device.

- Basic scan loop confirmed against physical tags using iData calls only: powerSet, sessionModeSet, inventoryModelSet, readTagFromBuffer.

Deliverable: “Hello World” on both ends — Android reads a tag and logs a raw EPC; Odoo shell can create/query a manually entered rfid.tag.mapping row.

## Phase 2 — Odoo-Side Bridge Module + EPC Mapping (Week 2–3)

- rfid.tag.mapping model: epc (unique, indexed), product_id, barcode, serial_number, encoding_type (supplier / in_house / non_standard), lot_id (optional — never required, so an unmapped tag never blocks the unknown-EPC workflow).

- stock.barcode.rfid.scan audit model: epc, rssi, resolved product/lot, status (resolved / unknown / discrepancy), session_id, inventory_id, timestamps.

- POST /stock_barcode_rfid/scan: resolves EPC against rfid.tag.mapping; logs every scan; returns status.

- Server-side dedup: 2-second window, keyed on EPC.

- Three Ventor-pattern mapping scenarios: (1) supplier pre-encoded — barcode match, (2) in-house write — POST /write_tags batch-creates mappings, (3) non-standard EPC — manual serial_number entry + rescan.

- Unknown-EPC workflow: status='unknown' logged, never blocks the scan session; surfaced in a Discrepancies view for operator resolution.

- API key auth: validate Odoo API key against res.users inside the controller (auth='public' + manual check) — not a bare auth='bearer' declaration.

- Session/stream mechanism (SSE or long-poll) relaying resolved scans into the custom scan UI.

- Unit + integration tests: dedup window, EPC validation, all 3 mapping scenarios, unknown-EPC path.

Deliverable: POSTing an EPC via curl/Postman correctly resolves against a known mapping, or is logged as unknown — and either way is visible in an open Inventory Adjustment session in the custom scan UI.

## Phase 3 — Android Scanning App (Week 3–5)

- Core scan loop against the iData T1UHF SDK: powerSet, sessionModeSet, inventoryModelSet, readTagFromBuffer. No Zebra/DataWedge classes, imports, or references anywhere in the codebase.

- Client-side dedup (in-memory, tunable window).

- RSSI-based software filtering, exposed as a tunable setting.

- Batch-and-throttle logic to the Odoo bridge.

- Auth: Odoo API key stored in Android Keystore, device paired to a specific Odoo user.

- Operator UI: live unique-tag count, manual flush/sync, connection-health indicator, calibration-preset selector.

- Offline queue: SQLite buffer on Wi-Fi drop, resync on reconnect.

Deliverable: operator walks a shelf, watches the tag count climb live, and sees it reflected in the custom Odoo scan UI in near real time.

## Phase 4 — RFID Calibration (Week 5–6, parallel to late Phase 3)

This phase determines whether the project succeeds. RFID is only better than barcode if it's tuned correctly. Accuracy is locked before throughput is tuned — never the reverse.

| Step | Action | Target Output |
| --- | --- | --- |
| 1 | Baseline test: max power, Session 0, Multi-label mode | Establish worst-case over-read radius |
| 2 | Step power down (powerSet) in ~4dBm increments at real bin distance | Lowest power that still reliably reads every in-zone tag |
| 3 | Switch Session 0→1→2 (sessionModeSet), re-test dupe rate per sweep | Session value minimizing redundant reads without missing tags |
| 4 | Test inventory modes (inventoryModelSet): Multi-label vs Adaptive power-saving vs Fast-read | Best mode for actual scan pattern |
| 5 | RSSI-floor sweep in Android app | Threshold that cuts cross-shelf reads without cutting real ones |
| 6 | Combine best settings; A/B RFID vs manual count, 5+ trials, varied shelf densities | Documented accuracy % and time-savings % |
| 7 | Throughput pass: tune Q-value/anti-collision, EPC-only reads, profile Android dedup + batch sizing + bridge throughput — power/session/RSSI floor untouched | Maximum sustained scan speed within the accuracy-safe envelope from Steps 1–6 |
| 8 | Re-run the Step 6 accuracy A/B after Step 7 tuning | Confirms throughput tuning did not regress accuracy — required sign-off before a profile ships |

Deliverable: a written calibration profile (power, session, mode, RSSI floor, Q-value/throughput settings) per shelf/zone type, baked into the Android app as selectable presets.

## Phase 5 — Integration Testing (Week 6–7)

- End-to-end test: RFID scan → Android dedup → Odoo bridge → custom scan UI → stock.quant adjustment, verified against the audit trail.

- Multi-user test: two devices scanning into two different sessions concurrently, no cross-talk.

- Failure-mode testing: server restart mid-scan, network drop, garbage EPC, unknown EPC.

- Load test: dense shelf sweep (200+ tags), no dropped scans, acceptable controller latency.

- Security pass: scan endpoint cannot inject arbitrary stock adjustments without a valid authenticated session.

- Performance targets: POST /scan <100ms p95, ≥50 EPCs/sec per session.

Deliverable: signed-off test report; known-issues list triaged into “fix before pilot” vs. “acceptable for pilot.”

## Phase 6 — Pilot / UAT (Week 7–8) — SCOPE END

- Run pilot on one real warehouse zone, RFID-tagged, operator trained, barcode kept as fallback.

- Shadow-run: RFID counts logged but not authoritative; compare against manual counts for 3–5 working days.

- Collect operator feedback on device ergonomics, scan speed, false-read incidents.

- Adjust calibration profiles based on real floor conditions (always differs from Phase 4 lab tests).

Deliverable: go/no-go decision with real accuracy numbers, not lab numbers. This is the final deliverable of the OJT placement.

## Phase 7 — Production Rollout — OUT OF SCOPE (reference only)

Not part of this OJT engagement. Recorded here only so the pilot's handoff notes have somewhere to point. Would include: production-grade infra (dedicated Postgres + backups, HTTPS via Nginx/Traefik), staging environment, phased zone-by-zone rollout, then evaluation of Receiving/Delivery workflows.

# 4. Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| RFID over-reads cause incorrect stock adjustments | High | Phase 4 calibration mandatory before pilot use; RSSI floor + power tuning per zone; Step 8 re-validation before any profile ships. |
| Zebra/DataWedge references creep back into code or docs | High | This has recurred in every prior draft. Grep for zebra¦datawedge before accepting any generated code or document. |
| Barcode Nomenclature / stock.lot.name approach creeps back in | High | Recurred in two of the four source documents reviewed 2026-08-23. Section 2 of this document is now the single check against that regression. |
| stock_barcode / Barcode Nomenclature dependency assumed available | High | Confirmed unavailable on Community; custom OWL/QWeb UI is the only primary path, SQLite+XML-RPC is the contingency. |
| iData T1UHF SDK unavailable or incompatible | High — Week 1 blocker | Test immediately in Phase 1, Day 1–2. This determines whether the rest of the roadmap holds. |
| auth='bearer' implemented literally, fails at runtime | Medium | Corrected in Section 2/5: use auth='public' + manual API-key check inside the controller. |
| Warehouse Wi-Fi dead zones drop scans mid-count | Medium | Offline queue (SQLite) + resync in Android app, Phase 3. |
| Operators revert to barcode out of habit/distrust | Medium | Pilot phase with visible accuracy metrics builds trust before any mandate. |
| Tag cost/durability in warehouse conditions | Low–Medium | Pilot with actual tag stock before any bulk order (out of OJT scope). |
| SSE/long-poll viability on Odoo 19 Community untested | High | The live scan UI’s success criterion depends on this untested assumption. Validate SSE/long-poll behavior early in Phase 2 (Week 2–3); fall back to the documented Section 7 SQLite + XML-RPC/JSON-RPC contingency if it proves unreliable under load or reconnect scenarios. |
| Single-developer bandwidth across Android, Odoo backend, and RFID calibration | Medium–High | One developer covering all three tracks over 8 weeks is a real schedule/quality risk. Mitigate by strictly sequencing per the Phased Roadmap (no parallel scope creep beyond the Phase 3/4 overlap already planned), flagging slippage early to the supervisor, and treating Phase 4 calibration as non-negotiable before throughput work. |

# 5. API Authentication — Correction

Prior drafts declared @http.route(..., auth='bearer', ...). Odoo's route decorator does not ship a 'bearer' auth type — the built-in values are 'user', 'public', and 'none'. The corrected pattern:

@http.route('/stock_barcode_rfid/scan', auth='public', type='json', methods=['POST'], csrf=False)
def scan(self, **kwargs):
    api_key = request.httprequest.headers.get('Authorization', '').removeprefix('Bearer ').strip()
    user = request.env['res.users'].sudo()._check_credentials_from_api_key(api_key)  # custom helper
    if not user:
        return {'error': 'Unauthorized'}, 401
    # proceed as user.with_user(user).env[...]

Odoo 17+ ships a native res.users.apikeys model (Settings > Users > API Keys). The custom helper above should look up the key's hash against that table rather than storing raw keys anywhere — do not roll a bespoke API-key table.

# 6. Rough Timeline

| Weeks | Milestone |
| --- | --- |
| Week 1 | Discovery & requirements lock (complete) — environment & foundations |
| Week 1–2 | Environment & foundations; iData T1UHF SDK integrated |
| Week 2–3 | Odoo bridge module + rfid.tag.mapping + 3 Ventor-pattern scenarios |
| Week 3–5 | Android scanner app |
| Week 5–6 | Calibration (parallel to late Android work) |
| Week 6–7 | Integration testing |
| Week 7–8 | Pilot / UAT — OJT scope ends here |

~8 weeks to a validated single-zone pilot, assuming the iData T1UHF SDK validates in Week 1 — the single largest schedule risk in the whole plan.

# 7. Contingency Plan — Local Buffer + XML-RPC Sync

Status: documented fallback, not the current primary path. Revisit only if the custom OWL/QWeb scan UI stalls or slips the timeline.

- iData T1UHF reads a tag → EPC → Android app.

- Android app writes scan rows to a local SQLite buffer (not a flat file — concurrent read/write safety).

- A sync process batch-calls Odoo's execute_kw (XML-RPC) or JSON-RPC to update stock.quant / stock.move.line.

- Optional: export the buffer to XLSX/CSV on a schedule for human-readable audit logs, without making the spreadsheet the live data store.

Odoo's XML-RPC/JSON-RPC API is identical across Community and Enterprise — it is not gated by edition — so this path carries zero stock_barcode / Enterprise risk, at the cost of operators losing a live in-Odoo scan screen.

# 8. Immediate Next Steps

- Acquire and validate the iData T1UHF SDK against the physical device — the Week 1 critical path item.

- Stand up the Odoo 19 Docker Compose dev environment.

- Scaffold the stock_barcode_rfid module and the rfid.tag.mapping / stock.barcode.rfid.scan models exactly as specified in Section 2.

- Rebuild the day-by-day tracker against this document (see companion file: SEAN_TRACKER_MASTER.xlsx).

# 9. Addendum — Architecture Pivot (2026-08-26)

Per Vin’s explicit direction, the custom-module architecture in Section 2 (rfid.tag.mapping model, POST /stock_barcode_rfid/scan controller, server-side EPC resolution, custom OWL/QWeb scan UI over SSE/long-poll) is superseded, effective this addendum, by the direct-integration approach validated in a parallel session (“Option 3”): the Android app calls Odoo’s XML-RPC/JSON-RPC API directly, resolves EPCs against stock.lot.name, and writes stock.quant / stock.move updates itself. No custom controller or bridge module sits in between.

This reverses a decision this document previously treated as settled. The Risk Register (Section 4) explicitly flagged “Barcode Nomenclature / stock.lot.name approach creeps back in” as a High-impact regression, on the basis that this pattern cannot represent status=’unknown’ for an unmapped EPC. That limitation still applies: under this pivot, an unrecognized tag has no defined path to being logged and surfaced for operator review, which is how Success Criterion 5 (“Unknown/unmapped EPCs never silently dropped”) was originally satisfied. If that criterion is still required, it must be re-solved at the Android app layer (e.g. the app itself logs and surfaces XML-RPC lookups that return no match) rather than relying on this document’s original design.

Sections superseded by this addendum: Section 2’s “Custom model” and “In-Odoo scan UI” rows; Section 8’s next step to scaffold stock_barcode_rfid per Section 2. The rfid.tag.mapping and stock.barcode.rfid.scan models and the scan controller already committed to the repository as of 2026-08-26 are retained in source control but are no longer the active integration path pending further direction.